|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Reference Timeline Retrospective Study** | | | | | | | | | | | |
| **Calendar Month** | **Aug-Nov 2020** | **Nov** | **Dec** | **Jan** | | **Feb** | **Mar** | **Apr** | **May** | **Jun** | **Jul** |
| **Month of Study** | **1-3** | **4** | **5** | **6** | | **7** | **8** | **9** | **10** | **11** | **12** |
| **Primary site/ PI activity** | Prepare project with mentors | Present project at FPRN® Session, Decision by Nov 30th | IRB preparation at primary site | | | Submit IRB | IRB approval at primary site  Work in Progress Presentation at SGS | | Data Mining at primary site  Manuscript Introduction and Methods Writing | | |
| **Secondary site activity** | [No secondary sites yet] | | | | Identify secondary sites | | IRB submissions secondary sites | | IRB approval Secondary Sites | | |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Reference Timeline Retrospective Study** | | | | | | | | | |
| **Calendar Month** | **August 2021** | **Sep** | **Oct** | **Nov** | **Dec** | **Jan** | **Feb** | **Mar** | **Apr** |
| **Month of Study** | **13** | **14** | **15** | **16** | **17** | **18** | **19** | **20** | **21** |
| **Primary site/PI activity** | Finish data mining at 1° site  Finish writing Intro, Methods | | Skeleton tables and results section of manuscript  Collect data from finished sites  Work in progress presentation at AAGL | | | Data Clean and Finalize Analysis Plan | Analyze Data and Fill in Results | Complete Discussion and Send Manuscript to Team for Final Revisions | |
| **Secondary site activity** | Data mining secondary sites | | | | | All Data to Primary Site | Other authors completing writing as assigned by PI | | Send final draft revisions to PI |